## Design Department Tracker
DESIGN DEPARTMENT TRACKER – TAMAKOSHI V HYDROELECTRIC PROJECT (LOT-1)
S.No. | Send Date | Letter No. | Employer's Ref. | Engineer's Ref. | Sinohydro Ref. | Subject | Attachment | Sinohydro's Reply Ref. | Department | Location | Remarks | Status | Notes
1 | 02-06-2024 | LOT-01/SINOHYDRO-KSNS-JV/015 | N/A | N/A | N/A | Request for Progress Update on Mobilization, Basic Design, Temporary Roads, and Preparation Works | N/A | N/A | Construction/Design | N/A | N/A | Other
2 | 04-07-2024 | LOT-01/SINOHYDRO-KSNS-JV/025 | N/A | N/A | TKV/COM/2024/037 TKV/COM/2024/036 TKV/COM/2024/028 TKV/COM/2024/027 TKV/COM/2024/026 TKV/COM/2024/025 TKV/COM/2024/023 TKV/COM/2024/019 TKV/COM/2024/018 TKV/COM/2024/011 TKV/COM/2024/009 TKV/COM/2024/006 TKV/COM/2024/005 TKV/COM/2024/004 | Response Letter | N/A | TKV/COM/2024/151 | Design/Schedue/Technical/Construction | N/A | N/A | Other
3 | 05-07-2024 | LOT-01/SINOHYDRO-KSNS-JV/027 | N/A | N/A | TKV/COM/2024/032 | Project Design Management Plan | Project Design Management Plan | N/A | Design | N/A | N/A | Other
4 | 05-07-2024 | LOT-01/SINOHYDRO-KSNS-JV/028 | N/A | N/A | TKV/COM/2024/021 | Submission of Preliminary Head Loss Calculation | N/A | TKV/COM/2025/327 | Design | N/A | N/A | Accept
5 | 09-07-2024 | LOT-01/SINOHYDRO-KSNS-JV/030 | N/A | N/A | N/A | Minutes of Meeting | Minutes of Meeting-Discussion on Progress and Challenges Faced on Lot-1 | TKV/COM/2025/227 | Contract/Design | N/A | No Need to Reply. | Other
6 | 07-08-2024 | LOT-01/SINOHYDRO-KSNS-JV/046 | N/A | N/A | TKV/COM/2024/048 | Review and Comments on Site Investigateion Proposals | N/A | TKV/COM/2024/084 TKV/COM/2025/220 | Design | N/A | N/A | Other
7 | 05-09-2024 | LOT-01/SINOHYDRO-KSNS-JV/061 | N/A | N/A | TKV/COM/2024/084 | Approval of Revised Site Investigation Proposal | 1) Investigation Proposal's Report-47 Pages 2) Response to Comment- 2 Pages 3) Appendix- Location Map of Drill Holes- 5 Pages | Approve TKV/COM/2025/220 TKV/COM/2025/450 TKV/COM/2025/428 TKV/COM/2025/405 TKV/COM/2025/500 | Design | N/A | No Need to Reply. | Other
8 | 12-09-2024 | LOT-01/SINOHYDRO-KSNS-JV/066 | N/A | N/A | TKV/COM/2024/093 | Review and Approval of Revised Adit-1 Reports and Drawings of Tunnel | 1) Detailed Design Report of Rock Support Analysis of Adit-1 Tunnel 2) Drawing of Adit-1 General Arrangement 3) Drawing of Adit-1 Excavation and Support Details 4) Drawing of Adit-1 ISHB 150 Details 5) Comments and Response Regarding the Adit-1 | TKV/COM/2025/242 TKV/COM/2025/394 | Design | Adit-1 | No Need to Reply. | A
9 | 12-11-2024 | LOT-01/SINOHYDRO-KSNS-JV/104 | N/A | N/A | TKV/COM/2024/125 | Review and Approval of Revised Adit-4 Reports and Drawings for Portal & Tunnel | N/A | TKV/COM/2024/167 TKV/COM/2025/186 TKV/COM/2025/214 | Design | Adit-4 | Approved | A
10 | 08-12-2024 | LOT-01/SINOHYDRO-KSNS-JV/112 | N/A | LOT-01/SINOHYDRO-KSNS-JV/110 | TKV/COM/2024/127 | Review and Approval of MAT and CVT Reports and Drawings for Portal and Tunnel | 1) Detail Design Report of Rock Support Analysis of MAT and CVT Portal report-32 pages 2) Excavation Support Design of MAT and CVT Portal report- 30 pages 3) Drawing of MAT General Arrangement Plan, Profile and Typical Sections-3 pages 4) Drawing of MAT and CVT Portal Excavation-7 pages 5) Drawing of Main Access Tunnel Excavation and Rock Support Details-4 pages 6) Drawing of Main Access Tunnel ISHB 150 Details- 4 Pages 7) Drawing of MAT and CVT Geological Plan and Section -5 Pages 8) Response to comments-2 Pages | TKV/COM/2024/168 TKV/COM/2025/186 | Design | MAT and CVT | Approved | A
11 | 13-12-2024 | LOT-01/SINOHYDRO-KSNS-JV/118 | DOLSAR CSPDR JV/078 Engineer to Employer | LOT-01/SINOHYDRO-KSNS-JV/092 | TKV/COM/2024/145 TKV/COM/2024/142 TKV/COM/2024/128 TKV/COM/2024/119 | Response to Requirement for Changes in Headpond Structure Design and Notice of Claim | N/A | TKV/COM/2025/327 | Design/Contract | N/A | N/A | Other
12 | 20-12-2024 | LOT-01/SINOHYDRO-KSNS-JV/122 | N/A | LOT-01/SINOHYDRO-KSNS-JV/092 LOT-01/SINOHYDRO-KSNS-JV/071 | TKV/COM/2024/142 TKV/COM/2024/119 TKV/COM/2024/077 | Engineer's Review of Draft Basic Desiqn Report | a. Appendix 1. Hydropower Tunnel Failures - Risks and Causes b. Appendix 2. Comment Sheet - R02 c. Appendix 3.Basic Design Report (Document No: TKV-CR/BD-02 | TKV/COM/2025/213 TKV/COM/2025/327 TKV/COM/2025/377 TKV/COM/2025/410 TKV/COM/2025/411 | Design | Basic Design | N/A | Other
13 | 24-12-2024 | LOT-01/SINOHYDRO-KSNS-JV/126 | N/A | N/A | N/A | Submission of Shop Drawings as per Contractual Requirements | N/A | TKV/COM/2024/178 TKV/COM/2025/502 | Design | N/A | N/A | Other
14 | 06-01-2025 | LOT-01/SINOHYDRO-KSNS-JV/138 | N/A | LOT-01/SINOHYDRO-KSNS-JV/121 | TKV/COM/2025/185 TKV/COM/2024/163 | Response to the Contractor’s Proposal for New Design of Adit-3. | N/A | TKV/COM/2025/190 TKV/COM/2025/277 TKV/COM/2025/296 TKV/COM/2025/300 TKV/COM/2025/339 | Contract/Design | N/A | N/A | Other
15 | 08-01-2025 | LOT-01/SINOHYDRO-KSNS-JV/140 | N/A | LOT-01/SINOHYDRO-KSNS-JV/126 | TKV/COM/2024/178 TKV/COM/2024/165 | Response to Submission of Shop Drawings and Pending Approvals | N/A | TKV/COM/2025/502 | Design | Shop Drawing | N/A | Other
16 | 09-01-2025 | LOT-01/SINOHYDRO-KSNS-JV/141 | N/A | LOT-01/SINOHYDRO-KSNS-JV/138 | TKV/COM/2024/157 TKV/COM/2024/163 TKV/COM/2025/185 | Review of Adit-3 Reports and Drawings for Portal and Tunnel | N/A | N/A | Design | Adit-3 | N/A | RFC
17 | 09-02-2025 | LOT-01/SINOHYDRO-KSNS-JV/174 | N/A | LOT-01/SINOHYDRO-KSNS-JV/164 LOT-01/SINOHYDRO-KSNS-JV/138 LOT-01/SINOHYDRO-KSNS-JV/121 | TKV/COM/2025/190 TKV/COM/2025/185 TKV/COM/2024/163 | Response to Repeated Submissions Regarding the Issues related to Adit-3 | N/A | TKV/COM/2025/277 TKV/COM/2025/296 TKV/COM/2025/300 TKV/COM/2025/339 | Contract/design | N/A | N/A | Other
18 | 28-02-2025 | LOT-01/SINOHYDRO-KSNS-JV/186 | N/A | N/A | TKV/COM/2025/209 TKV/COM/2025/199 | Review of Letter 199 and Letter 209- Adit-2 Reports and Drawings for Portal & Tunnel | N/A | N/A | Design | Adit-2 | N/A | RFC
19 | 07-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/188 | N/A | N/A | TKV/COM/2025/224 | Response to Meeting Request. | N/A | N/A | Design | N/A | No Need to Reply. | Other
20 | 27-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/207 | N/A | N/A | TKV/COM/2025/213 | Response to the Comment on Headrace Tunnel Design in Basic Design Report | N/A | N/A | Design | HRT | N/A | RFC
21 | 30-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/213 | N/A | N/A | TKV/COM/2025/238 | Response to Submission of Drawings and Report of Cable & Ventilation Tunnel (CVT) | Annotated Draw'ing & Report - CVT | TKV/COM/2025/290 TKV/COM/2025/336 TKV/COM/2025/359 | Design | CVT | N/A | AAN
22 | 01-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/217 | N/A | DOLSAR_CSPDR_JV/122 Email Circulated to the all stakeholders on 19 February 2025, timestamped @ 11:24 PM | N/A | Notification for Progress Review Meeting and Follow-up on Outstanding Issues Ahead of the Second Monthly Progress Meeting | N/A | N/A | Design/Planning and Schedule/Construction | N/A | No Need to Reply. | Other
23 | 03-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/222 | N/A | N/A | TKV/COM/2025/242 | Response to Resubmission of Drawing and Report for Adit-1 | Annotated Drawing & Reporl - Adit-1 | TKV/COM/2025/274 TKV/COM/2025/290 TKV/COM/2025/394 | Design | Adit-1 | N/A | AAN
24 | 03-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/223 | N/A | N/A | TKV/COM/2025/236 | Response to Contractor’s Request for Confirmation on Land Acquisition and Tree Cutting Permits for Access Road Works. | N/A | TKV/COM/2025/467 | QA/Design | N/A | N/A | Other
25 | 08-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/226 | N/A | N/A | TKV/COM/2025/249 | Response to Resubmission of Drawing and Report for Adit-4 Tunnel | N/A | TKV/COM/2025/270 | Design | Adit-4 | N/A | AAN
26 | 11-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/231 | N/A | N/A | TKV/COM/2025/256 | Response to Submission of Drawing and Report for Main Access Tunnel (MAT). | Annotated Drawing & Report – Main Access Tunnel (MAT) | TKV/COM/2025/290 | Design | MAT | N/A | AAN
27 | 11-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/232 | N/A | N/A | TKV/COM/2025/262 | Response to Resubmission of Drawings and Report for Adit-2 Portal and Tunnel. | Annotated Drawing & Report – Adit-2 | TKV/COM/2025/290 TKV/COM/2025/322 TKV/COM/2025/385 | Design | Adit-2 | N/A | AAN
28 | 15-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/238 | N/A | N/A | TKV/COM/2025/263 | Response to Submission of Drawing and Report of Powerhouse Cavern | Report and Drawing | TKV/COM/2025/291 TKV/COM/2025/361 TKV/COM/2025/403 | Design | Powerhouse Cavern | Approved but Contractor decide another submission | A
29 | 16-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/239 | N/A | N/A | TKV/COM/2025/270 | Response to Submission of Drawings and Report for Adit-4 Tunnel | Annotated Drawing & Report – Adit-4 | TKV/COM/2025/290 TKV/COM/2025/349 TKV/COM/2025/358 | Design | Adit-4 | N/A | AAN
30 | 18-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/243 | N/A | N/A | TKV/COM/2025/272 | Response to Submission of Drawing and Report for Connecting Tunnel | Attachment:Annotated Drawing & Report- Connecting Tunnel | TKV/COM/2025/290 | Design | Connecting Tunnel | N/A | AAN
31 | 21-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/245 | N/A | N/A | TKV/COM/2025/273 | Response to Submission of Drawing and Report of Tailrace Outlet Portal | Attachment:Annotated Drawing & Report- Tailrace outlet Portal | TKV/COM/2025/290 | Design | Tailrace, outlet portal | N/A | AAN
32 | 24-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/246 | N/A | N/A | TKV/COM/2025/274 | [Reply] Response to Submission of Drawing and Report for Adit-1 | Approved Drawing and Reports of the Adit-1 Tunnel | TKV/COM/2025/297 TKV/COM/2025/394 | Design | Adit-1 | N/A | A
33 | 27-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/249 | N/A | N/A | TKV/COM/2025/290 | Comments on the Provision of Centralizers for Rock Bolts | N/A | N/A | Design | N/A | N/A | Other
34 | 29-04-2025 | LOT-01/SINOHYDRO-KSNS-JV/251 | N/A | N/A | TKV/COM/2025/291 | Response to Submission of Drawings and Report of Powerhouse Cavern | N/A | TKV/COM/2025/361 TKV/COM/2025/403 | Design | N/A | N/A | Other
35 | 03-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/256 | N/A | LOT-01/SINOHYDRO-KSNS-JV/246 | TKV/COM/2025/297 | Response to Submission of Report and Drawing for Adit-1 Construction Tunnel/Access. | DETAIL DESIGN REPORT OF ROCK SUPPORT ANALYSIS OF ADIT-1TUNNEL | TKV/COM/2025/308 TKV/COM/2025/324 TKV/COM/2025/394 | Design | Adit-1 | N/A | A
36 | 07-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/259 | N/A | N/A | TKV/COM/2025/260 | Response to Submission of Revised Steel Lining Reports and Drawings for Pressure Tunnel and Shaft | N/A | TKV/COM/2025/686 | Design | N/A | N/A | Other
37 | 15-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/271 | N/A | LOT-01/SINOHYDRO-KSNS-JV/256 | TKV/COM/2025/308 TKV/COM/2025/297 | Response to Submission of Revised Report and Drawing for Adit-1 Construction Tunnel/Access | N/A | TKV/COM/2025/394 | Design | N/A | N/A | AAN
38 | 27-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/278 | N/A | LOT-01/SINOHYDRO-KSNS-JV/174 LOT-01/SINOHYDRO-KSNS-JV/138 LOT-01/SINOHYDRO-KSNS-JV/121 | TKV/COM/2025/296 TKV/COM/2025/190 TKV/COM/2025/185 TKV/COM/2024/163 TKV/COM/2024/157 | Response to the Contractor’s Proposal for Relocation of Adit-3 Portal | N/A | TKV/COM/2025/339 | Design/Contract | N/A | N/A | Other
39 | 30-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/280 | N/A | N/A | TKV/COM/2025/315 TKV/COM/2024/142 | Response to Modification on the Tailrace Tunnel and Tailrace Surge Shaft | N/A | N/A | Design | N/A | N/A | Other
40 | 30-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/282 | N/A | N/A | TKV/COM/2025/319 | Response to Submission of Design Change Notice (DCN) for Weep Hole Detail Design Drawing for Underground Cavern | Approved Design Change Notice | N/A | Design | DCN-01 | No Need to Reply. | A
41 | 30-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/283 | N/A | LOT-01/SINOHYDRO-KSNS-JV/262 | TKV/COM/2025/324 TKV/COM/2025/286 | Response to Contractor’s Response to Absence of Steel Ribs/Lattice Girders in Adit-1 Bifurcation , Engineer’s Response to NCR Rejection | N/A | TKV/COM/2025/355 TKV/COM/2025/394 | Design/QC | N/A | N/A | Other
42 | 30-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/284 | N/A | N/A | N/A | Finalization of Revised Basic Design for Lot-2 Tender Documents | N/A | TKV/COM/2025/376 | Design/Contract | N/A | N/A | Other
43 | 31-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/287 | N/A | N/A | TKV/COM/2025/334 | Response to Submission of Report and Drawing for the Spillway Tunnel | N/A | TKV/COM/2025/409 | Design | Spillway Tunnel | No Need to Reply. | A
44 | 31-05-2025 | LOT-01/SINOHYDRO-KSNS-JV/288 | N/A | N/A | TKV/COM/2025/336 | Response to Submission of Design Change Notice (DCN) for Cable and Ventilation Tunnel | Report and Drawing | N/A | Design | DCN-02 | No Need to Reply. | A
45 | 03-06-2025 | LOT-01/SINOHYDRO-KSNS-JV/291 | N/A | LOT-01/SINOHYDRO-KSNS-JV/278 LOT-01/SINOHYDRO-KSNS-JV/174 | TKV/COM/2025/300 | Response to Contractor’s Submission Requesting for Advice and Instruction to Initiate Access Road Construction for Adit-3 Portal | N/A | N/A | Design/Contract | Adit-3 | N/A | Other
46 | 05-06-2025 | LOT-01/SINOHYDRO-KSNS-JV/300 | N/A | N/A | TKV/COM/2025/342 | Response to Submission of Design Change Notification-003 (DCN-25-C-003) for Substitution of Lattice Girders/Steel Rib with RRS at Intersection on MAT. | DCN-25-C-003 Drawing Report | N/A | Design | DCN-03 | N/A | AAN
47 | 06-06-2025 | LOT-01/SINOHYDRO-KSNS-JV/305 | N/A | LOT-01/SINOHYDRO-KSNS-JV/212 | TKV/COM/2025/318 | Response to Correspondence Regarding Access to Site and Constructive Acceleration Proposal – Surge Tank | N/A | N/A | Design/Contract | N/A | N/A | Other
48 | 18-06-2025 | LOT-01/SINOHYDRO-KSNS-JV/319 | N/A | LOT-01/SINOHYDRO-KSNS-JV/068 | TKV/COM/2054/331 TKV/COM/2024/086 | Response to the Request for Data from Contractor of Lot-2 | N/A | TKV/COM/2025/376 TKV/COM/2025/404 | Design | N/A | N/A | Other
49 | 24-06-2025 | LOT-01/SINOHYDRO-KSNS-JV/323 | N/A | N/A | TKV/COM/2025/340 | Response to Submission of Drawing and Report of the Headpond Cavern | 1.Details Design Report of Rock Support of Analysis of Headpond Cavern 2.Plan and Profile of Headpond Cavern 3.Excavation and Rock support Details for Headpond Cavern 4.Instrumentation Details for Headpond Cavern | N/A | Design | Headpond Cavern | N/A | Approved
50 | 25-06-2025 | LOT-01/SINOHYDRO-KSNS-JV/324 | N/A | LOT-01/SINOHYDRO-KSNS-JV/306 LOT-01/SINOHYDRO-KSNS-JV/278 LOT-01/SINOHYDRO-KSNS-JV/174 LOT-01/SINOHYDRO-KSNS-JV/138 LOT-01/SINOHYDRO-KSNS-JV/121 | TKV/COM/2025/353 TKV/COM/2025/339 TKV/COM/2025/296 TKV/COM/2025/190 TKV/COM/2025/185 TKV/COM/2024/163 TKV/COM/2024/157 | Response to Contractor’s Proposals– Relocation of Adit‑3 Portal and Access Road | N/A | N/A | Design/Contract | N/A | N/A | Other
51 | 01-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/330 | N/A | LOT-01/SINOHYDRO-KSNS-JV/324 LOT-01/SINOHYDRO-KSNS-JV/306 LOT-01/SINOHYDRO-KSNS-JV/291 LOT-01/SINOHYDRO-KSNS-JV/278 LOT-01/SINOHYDRO-KSNS-JV/174 LOT-01/SINOHYDRO-KSNS-JV/138 LOT-01/SINOHYDRO-KSNS-JV/121 | TKV/COM/2025/354 TKV/COM/2025/353 TKV/COM/2025/339 TKV/COM/2025/296 TKV/COM/2025/190 TKV/COM/2025/185 TKV/COM/2025/163 TKV/COM/2025/157 | Response to Contractor’s Resubmission of Report and Drawing for Adit‑3 Tunnel and Portal | N/A | N/A | Design/Contract | N/A | N/A | Other
52 | 01-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/331 | N/A | LOT-01/SINOHYDRO-KSNS-JV/061 | TKV/COM/2025/367 | Response to Contractor’s Request for Approval of Site Investigation Proposal for Headpond Area | N/A | TKV/COM/2025/428 | Design/Geology | N/A | N/A | Other
53 | 03-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/333 | N/A | N/A | TKV/COM/2025/385 | Response to Submission of Design Change Notice (DCN-25-C-009) Related to Turning Bay in Adit-2 Tunnel | Approved DCN-25-C-009 | N/A | Design | N/A | N/A | Approved
54 | 03-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/335 | N/A | N/A | TKV/COM/2025/382 | Response to Submission of Drawing and Report of Surge Ventilation Tunnel and Portal | Approved Report and Drawing | N/A | Design | N/A | N/A | Approved
55 | 04-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/336 | N/A | LOT-01/SINOHYDRO-KSNS-JV/061 | TKV/COM/2025/274 | Response to Revised Site Investigation Proposal – Takeoff Yard and Bypass Station | N/A | N/A | Design/Geology | N/A | N/A | Other
56 | 06-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/339 | N/A | N/A | TKV/COM/2025/359 | Response to Submission of Design Change Notice (DCN-25-C-007) for Adjusting of Elevation and Slope of Access to CVT | N/A | N/A | Design | N/A | N/A | AAN
57 | 06-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/340 | N/A | LOT-01/SINOHYDRO-KSNS-JV/252 | TKV/COM/2025/370 | Response to Contractor’s Submission of Site Investigation Method Statement | Method statement of Geotechnical Investigation | N/A | Geology/Design | N/A | N/A | Approved
58 | 09-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/351 | N/A | N/A | TKV/COM/2025/349 | Response to Submission of Design Change Notice (DCN-25-C-004) for Rock Support at Intersection at Adit-4 | Enclosure: Attachment 1: Comment & Reply Sheet for "Design Change Notice (DCN-25-C-004) for DetailDesign Report of Rock Support at intersection at Adi-4", Ref. Letter No. TKVCOM2025/349, dated 05June 2025 (3 pages) | N/A | Design | N/A | N/A | RFC
59 | 12-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/356 | N/A | LOT-01/SINOHYDRO-KSNS-JV/262 NCR:DOL-NEP-1053-MUS-GNL-NCR-005 | TKV/COM/2025/355 TKV/COM/2025/324 TKV/COM/2025/286 | Response to Contractor’s Submission of Design Change Notice (DCN-25-C-005) for Rock Support at Adit-1 Bifurcation | Design Change Note (DCN-25-C-005) | N/A | Design | N/A | N/A | AAN
60 | 12-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/359 | N/A | LOT-01/SINOHYDRO-KSNS-JV/279 | TKV/COM/2025/362 | Response to Contractor’s Notice of Claim due to Pilot (Test Adit) Tunnel Overbreak and Support Issues at CVT Intersection (VT-9) | N/A | TKV/COM/2025/651 | Design | N/A | N/A | Other
61 | 13-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/360 | N/A | LOT-01/SINOHYDRO-KSNS-JV/378 LOT-01/SINOHYDRO-KSNS-JV/319 LOT-01/SINOHYDRO-KSNS-JV/080 LOT-01/SINOHYDRO-KSNS-JV/068 LOT-01/SINOHYDRO-KSNS-JV/032 LOT-01/SINOHYDRO-KSNS-JV/016 | TKV/COM/2025/378 TKV/COM/2024/099 TKV/COM/2024/044 TKV/COM/2024/039 | Response to Clarification and Meeting Request Regarding Division of Scope of Works and Interface Management | N/A | TKV/COM/2025/441 | Design/QA/QC | N/A | N/A | Other
62 | 13-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/362 | N/A | LOT-01/SINOHYDRO-KSNS-JV/319 LOT-01/SINOHYDRO-KSNS-JV/314 | TKV/COM/2025/376 | Response to Contractor’s Request for Interface Data from the Lot-2 Contractor and Head Loss Concerns and Clarification of Contractual Responsibilities | N/A | TKV/COM/2025/404 | Design/Contract | N/A | Draft | Other
63 | 14-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/365 | N/A | LOT-01/SINOHYDRO-KSNS-JV/351 | TKV/COM/2024/363 | Response to Contractor’s Submission of Design Change Notice (DCN-25-C-008): Replacement of Lattice Girder/Steel Rib with RRS-1 (Reinforced Ribs) at Main Access Tunnel (MAT). | Design Change Notice | N/A | Design | N/A | N/A | AAN
64 | 17-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/368 | N/A | N/A | TKV/COM/2025/403 | Response to Resubmission of Drawings and Reports of Powerhouse Cavern | Comment and Reply Sheet for the “Resubmission of Drawings and Report of the Powerhouse Cavern”, Ref. Letter TKV/COM/2025/403 dated 15 July 2025 | TKV/COM/2025/586 | Design | N/A | N/A | AAN
65 | 20-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/369 | N/A | N/A | TKV/COM/2024/406 | Response to Resubmission of Drawings and Reports of Rock Support for Power Station Tailrace Surge Tunnel | Detail Design Report of Rock Support of Power Station - Tailrace Surge Tunnel | N/A | Design | N/A | N/A | Approved
66 | 20-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/370 | N/A | N/A | TKV/COM/2024/409 | Response to Contractor’s Submission of Design Change Notice (DCN-25-C-010) Related to Sprayed Concrete and RRS-1 | SPILLWAY TUNNEL GENERAL PROJECT LAYOUT PLAN AND PROFILE | N/A | Design | N/A | N/A | AAN
67 | 25-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/375 | N/A | LOT-01/SINOHYDRO-KSNS-JV/288 | TKV/COM/2024/415 TKV/COM/2024/336 | Response to Contractor’s Submission of Design Change Note (DCN-25-C-011) – Cable and Ventilation Tunnel Typical Section and Tailrace Surge Tunnel Junction Rock Support Details | N/A | N/A | Design/Contract | N/A | N/A | AAN
68 | 26-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/376 | N/A | LOT-01/SINOHYDRO-KSNS-JV/061 | TKV/COM/2025/405 | Review and Instruction Regarding Revised Borehole Drilling Proposal at Powerhouse Area | N/A | TKV/COM/2025/450 TKV/COM/2025/500 | Design | N/A | N/A | Other
69 | 03-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/390 | N/A | LOT-01/SINOHYDRO-KSNS-JV/061 | TKV/COM/2025/428 TKV/COM/2025/331 | Approval of Modified Site Investigation Proposal for Head Pond | Annex 1: Proposed Borehole Location Map submitted by the Contractor | N/A | Design/Geology | N/A | N/A | Approved
70 | 09-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/400 | N/A | N/A | TKV/COM/2024/436 | Response to Resubmission of Detailed Design Report - Rock Support Analysis at Adit-1 Intersection & Reply Comments | Attachment 1: Comment & Reply Sheet for “Detailed Design Report-Rock Support Analysis at the Adit-1 Intersection and Reply Comments” (2 Pages). | N/A | Design | N/A | N/A | RFC
71 | 13-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/404 | N/A | N/A | TKV/COM/2025/439 | Response to Contractor’s Submission of Design Change Note (DCN-25-C-012) Design Value of Rockbolt Pullout Force for Underground Caverns | N/A | N/A | Design | N/A | N/A | Other
72 | 14-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/405 | N/A | LOT-01/SINOHYDRO-KSNS-JV/314 LOT-01/SINOHYDRO-KSNS-JV/319 LOT-01/SINOHYDRO-KSNS-JV/362 LOT-01/SINOHYDRO-KSNS-JV/366 | TKV/COM/2024/404 | Head Loss Deviation and Lot-2 Interface Data Responsibilities – Clarification of Contractual Obligations | N/A | TKV/COM/2025/458 | Contract/Design | N/A | N/A | Other
73 | 14-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/406 | N/A | N/A | TKV/COM/2024/424 | Response to Resubmission of Shop Drawing – Adit-1 Tunnel Excavation | Enclosure: Attachment 1: Comment & Reply Sheet for “Resubmission to Shop Drawing – Adit-1 Tunnel Excavation (1 Page). | N/A | Design | N/A | N/A | AAN
74 | 16-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/407 | N/A | LOT-01/SINOHYDRO-KSNS-JV/366 LOT-01/SINOHYDRO-KSNS-JV/314 | TKV/COM/2025/411 | Response to Contractor’s Claim regarding Proposed Enlargement of Head Race Tunnel Diameter | N/A | TKV/COM/2025/662 | Contract/Design | N/A | N/A | Other
75 | 18-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/410 | N/A | N/A | TKV/COM/2025/440 | Response to Contractor’s Submission of Transformer Excavation Drawing, Rock Support Report, Reply Sheet, and Phase Analysis Information | Enclosure: Attachment 1: Comment & Reply Sheet for Detail Design Report on Rock Support Analysis of Transformer Cavern (Doc. No.: TKC-CR-DD-TC-45-01) (2 Pages). | N/A | Design | N/A | N/A | Other
76 | 19-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/412 | N/A | N/A | TKV/COM/2025/443 | Response to Contractor’s Submission of Excavation and Drawing Report of Vertical Pressure Shaft | Enclosure: Attachment 1: Comment & Reply Sheet for Excavation and Drawing Report of Vertical Pressure Shaft (Doc. No.: TKC-CR-DD-PS-37-01) (1 Page). | N/A | Design | N/A | N/A | AAN
77 | 26-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/417 | N/A | N/A | TKV/COM/2025/459 | Response to Contractor’s Submission of Shop Drawing Excavation and Rock Support Details of Adit-02 | Enclosure Attachment 1: Comment & Reply Sheet for Shop Drawing Excavation and Rock Support Details of Adit-02 (1 Page). | N/A | Design | N/A | N/A | AAN
78 | 30-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/418 | N/A | LOT-01/SINOHYDRO-KSNS-JV/376 LOT-01/SINOHYDRO-KSNS-JV/061 | TKV/COM/2024/450 TKV/COM/2025/405 | Reply to Approval of Investigation Proposal for Powerhouse | N/A | TKV/COM/2025/500 | Geology/Design | N/A | N/A | Other
79 | 01-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/420 | N/A | N/A | TKV/COM/2025/464 | Response to Submission of Design Change Notice (DCN-25-C-013), Related to Headpond Convergence Monitoring and New Cross-Sections | 1.(DCN-25-C-013) related to the Headpond Convergence Monitoring & New Cross- Sections"-01Pages. 2. Attachement -Headpond Instrumentaiton 1-1 Pages. 3.Attachement -Headpond Instrumentaiton 2.-1 Pages. 4.Attachement -Headpond Instrumentaiton 3.-1 Pages. 5.Attachement -Headpond Instrumentaiton 4.-1Pages. 6.Attachment- 23C02_Headpond_Rock-Support.-11 Pages. | N/A | Design | N/A | N/A | A
80 | 01-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/421 | N/A | LOT-01/SINOHYDRO-KSNS-JV/408 NCR: DOL-NEP-1053-MUS-GNL-NCR-015 | TKV/COM/2025/462 | Response to Contractor’s Submission of Report and Drawing for Plug Structure at Test Adit and CVT Interface | Attachment-1, “Stability analysis report of plug structure at test Adit and cable and ventilation tunnel interface. (Doc. No.: TKV-CR-DD- PST-54-01)”, | N/A | Design | N/A | N/A | RFC
81 | 01-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/422 | N/A | N/A | TKV/COM/2025/463 | Response to Submission of Excavation and Rock Support Design and Drawing of VPS Bottom Cavern | Attachment – 1: Comments and Reply Sheet for the “Detail design report of rock support analysis of Vertical Pressure Shaft (VPS) Bottom Cavern (Doc. No.: TKV-CR-DD-PT-35-01)”, | N/A | Design | N/A | N/A | AAN
82 | 11-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/432 | N/A | N/A | TKV/COM/2025/474 | Response to Contractor’s Submission of Shop Drawing Connecting Tunnel Excavation and Rock Support | Attachment-1, Comments and Reply Sheet for the “Shop drawing of Connecting tunnel excavation and rock support” Ref. Letter, TKV/COM/2025/474 dated 31st August 2025. | N/A | Design | N/A | N/A | AAN
83 | 12-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/433 | N/A | N/A | TKV/COM/2025/483 | Response to Contractor’s Submission of DCN-25-C-015 Related to Waterways VPS Bottom Cavern Rock Support Details | 1. (DCN-25-C-015) Related to Waterways VPS Bottom Cavern Rock Support Details. .-04 Pages. 2. Attchement- VPS_Bottom_Cavern_Rock_Support.-09 Pages. | N/A | Design | N/A | N/A | A
84 | 17-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/443 | N/A | N/A | TKV/COM/2025/461 | Response to Request for Earthing Trench Layout Data – Powerhouse and Transformer Cavern | N/A | N/A | Contract/Design | N/A | N/A | Other
85 | 18-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/444 | N/A | N/A | TKV/COM/2025/488 | Response to Contractor’s Submission of Report and Drawing of Pull-Out Test | Attachment-1, Comments and Reply Sheet for the “Design Report of Rock Bolt Pull-Out Test (Doc. No. TKV-CR-DD-PT-01-01, Rev. 00)” Ref. Letter TKV/COM/2025/488 dated 5th September 2025 | N/A | Design | N/A | N/A | RFC
86 | 24-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/457 | N/A | N/A | TKV/COM/2025/481 | River Diversion Works at Tailrace Outlet – Acknowledgement of Draft Report & Advisory Comments | N/A | N/A | Design | N/A | N/A | Other
87 | 24-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/458 | N/A | LOT-01/SINOHYDRO-KSNS-JV/405 | TKV/COM/2025/458 TKV/COM/2025/404 | Response to Contractor’s Letter TKV/COM/2025/458 – Headrace Tunnel Enlargement & Lot-2 Interface Data Claims | N/A | TKV/COM/2025/641 TKV/COM/2025/662 TKV/COM/2025/769 | Contract/Design | N/A | N/A | Other
88 | 11-10-2025 | LOT-01/SINOHYDRO-KSNS-JV/471 | N/A | N/A | TKV/COM/2025/502 | Response to Contractor’s Submission and Preparation of Shop Drawings | N/A | N/A | Design | N/A | N/A | Other
89 | 11-10-2025 | LOT-01/SINOHYDRO-KSNS-JV/477 | N/A | N/A | TKV/COM/2025/486 | Use of 6 mm Thick Face Plates for Rock Dowels – Engineering Review and Recommendations | N/A | TKV/COM/2025/612 | Design | N/A | N/A | Other
90 | 19-10-2025 | LOT-01/SINOHYDRO-KSNS-JV/483 | N/A | N/A | N/A | Unauthorized Headrace Tunnel (HRT) Excavation – Notice of Non-Compliance (Lack of Design Submissions/Approval) | N/A | TKV/COM/2025/535 TKV/COM/2025/641 TKV/COM/2025/662 TKV/COM/2025/769 | Contract/Design | N/A | N/A | Other
91 | 08-11-2025 | LOT-01/SINOHYDRO-KSNS-JV/519 | N/A | N/A | TKV/COM/2025/550 TKV/COM/2025/256 | Response to Contractor’s Submission of Main Access Tunnel (Connecting Tunnel) Excavation and Support Drawings | N/A | N/A | Design | N/A | N/A | Other
92 | 08-11-2025 | LOT-01/SINOHYDRO-KSNS-JV/521 | N/A | LOT-01/SINOHYDRO-KSNS-JV/483 LOT-01/SINOHYDRO-KSNS-JV/458 | TKV/COM/2025/535 | Response to Contractor’s Submission of Revised HRT Design Drawings and Response to Notice of Non-Compliance | N/A | TKV/COM/2025/641 TKV/COM/2025/662 TKV/COM/2025/769 | Contract/Design | N/A | N/A | Other
93 | 23-11-2025 | LOT-01/SINOHYDRO-KSNS-JV/547 | N/A | N/A | TKV/COM/2025/566 | Response to Contractor’s Submission of Rock Support Design and Drawing of Upstream Manifold | Attachment 1: Comment & Reply Sheet for Rock Support Design and Drawing of Upstream Manifold (2 Pages). | N/A | Design | N/A | N/A | AAN
94 | 04-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/553 | N/A | N/A | TKV/COM/2025/586 | Response to Contractor’s Submission of Powerhouse Cavern Excavation and Support Drawing | Enclossure Attachment 1: Comment & Reply Sheet for Powerhouse Cavern Excavation and Support Drawing (2 Pages). | N/A | Design | N/A | N/A | AAN
95 | 10-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/560 | N/A | N/A | TKV/COM/2025/582 | Response to Contractor’s Submission of Bus Duct Tunnel Excavation and Support Drawing and Report | Attachment-1, Comments and Reply Sheet for the “Bus Duct Tunnel Excavation and Support Drawing and Report (3 pages) | N/A | Design | N/A | N/A | AAN
96 | 10-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/561 | N/A | N/A | TKV/COM/2025/605 | Submission of Technical Data Sheet and Preliminary Drawing for Hydraulic Butterfly Valve – Review and Comments | N/A | N/A | Design | N/A | N/A | Other
97 | 19-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/579 | N/A | LOT-01/SINOHYDRO-KSNS-JV/576 | TKV/COM/2025/604 | Response to Contractor's Submission of Cable and Ventillation Tunnel Invert Detail Drawing | Attachment 1: Comment & Reply Sheet for Cable and Ventilation Tunnel Invert Detail Drawing (2 Pages). | N/A | Design | N/A | N/A | RFC
98 | 21-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/581 | N/A | N/A | TKV/COM/2025/614 | Response to Contractor's Submission of Cable and Ventillation Tunnel Shop Drawing | Attachment 1: Comment & Reply Sheet for Cable and Ventilation Tunnel Shop Drawing (1 Page). | TKV/COM/2025/653 | Design | N/A | N/A | AAN
99 | 21-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/583 | N/A | N/A | TKV/COM/2025/632 | Response to Contractor’s Comments and Replies regarding Shop Drawings for Transformer Cavern Rock Support Details | Attachment 1: Comment & Reply Sheet for Shop Drawing for Transformer Cavern Rock Support Details (2 Pages) | TKV/COM/2025/652 | Design | N/A | N/A | AAN
100 | 23-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/584 | N/A | N/A | TKV/COM/2025/569 | Response to Contractor's Submission of Headrace Tunnel Excavation and Support Drawing and Report | Attachment 1: Comment & Reply Sheet for Headrace Tunnel Excavation and Support Drawing and Report (11 Pages) | N/A | Design | N/A | N/A | RFC
101 | 23-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/585 | N/A | N/A | TKV/COM/2025/634 | Response to Contractor's Comments and Response regarding Shop Drawing for Headpond Cavern Rock Support Details | Attachment 1: Comment & Reply Sheet for Shop Drawing for Headpond Cavern Rock Support Details (2 Pages) | N/A | Design | N/A | N/A | RFC
102 | 24-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/586 | N/A | N/A | TKV/COM/2025/640 | Response to Contractor’s Comments and Replies on Shop Drawings for Upstream Manifold Excavation and Rock Support Details | N/A | N/A | Design | N/A | N/A | Approved
103 | 24-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/589 | N/A | N/A | TKV/COM/2025/612 | Engineer's Response to Contractor's Submission Regarding Use of 6 mm Thick Face Plates for Rock Bolts | N/A | N/A | QC/Design | N/A | N/A | Other
104 | 30-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/602 | N/A | N/A | TKV/COM/2025/645 | Response to Contractor's Submission of Spillway Tunnel As - Built Drawing |  Attachment 1: Comment & Reply Sheet for Spillway Tunnel As-Built Drawing (1 Page).  Attachment 2: List of under-break chainages (1 page).  Attachment 3: Representative Cross-sections for Under-break (1 page). | N/A | Design | N/A | N/A | RFC
105 | 30-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/606 | N/A | N/A | TKV/COM/2025/591 | Submission of Upstream Manifold Hydro-Mechanical Design Reports and Drawings | Attachment 1: Comment & Reply Sheet for “Upstream Manifold Hydro-Mechanical Design Reports and Drawings” (6 Page). | TKV/COM/2025/712 | Design | N/A | N/A | AAN
106 | 01-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/608 | N/A | N/A | N/A | Request for Design Modification - Additional Reinforced Concrete Column in Transformer Cavern | Attachment 1: Drawing No. 46C01_Transformer_structure_Alternative-1 (Engineer’s Mark-Up for Transformer Cavern Column Addition) | N/A | Design | N/A | N/A | Other
107 | 01-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/609 | N/A | N/A | TKV/COM/2025/653 | Engineer's Response to Contractor's Submission of As - Built Drawing for Cable and Ventilation Tunnel Rock Support Details | Attachment 1: Comment & Reply Sheet for As-Built Drawing for Cable and Ventilation Tunnel Rock Support Details (2 Pages). | N/A | Design | N/A | N/A | RFC
108 | 04-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/616 | N/A | LOT-01/SINOHYDRO-KSNS-JV/583 | TKV/COM/2025/652 TKV/COM/2025/632 | Response to Contractor's Submission of As-Built Drawing for Transformer Cavern Rock Support Details | N/A | N/A | Design | N/A | N/A | RFC
109 | 04-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/617 | N/A | N/A | TKV/COM/2025/664 | Response to Contractor's Submission of Excavation and Rock Support Connecting Tunnel As-Built Drawing | Attachment 1: Comment & Reply Sheet for Excavation and Rock Support Connecting Tunnel As-Built Drawing (2 Pages). | N/A | Design | N/A | N/A | RFC
110 | 07-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/623 | N/A | N/A | TKV/COM/2025/672 | Response to Contractor's Submission of General Arrangement of Adit - 3 (Plan - Profile) Drawing | N/A | TKV/COM/2025/750 | Design | N/A | N/A | A
111 | 08-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/626 | N/A | LOT-01/SINOHYDRO-KSNS-JV/421 LOT-01/SINOHYDRO-KSNS-JV/408 NCR: DOL-NEP-1053-MUS-GNL-NCR-015 | TKV/COM/2025/660 TKV/COM/2025/462 | Response to Contractor's Submission of Test Tunnel Protection Structure General Arrangement Plan and Profile | N/A | N/A | Design | N/A | N/A | Other
112 | 10-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/627 | N/A | N/A | TKV/COM/2025/673 | Response to Contractor's Submission of Powerhouse Cavern Rock Support Details Shop Drawing and Reply-Comment | Attachment 1: Comment & Reply Sheet for Powerhouse Cavern Rock Support Details Shop Drawing (2 Pages). | N/A | Design | N/A | N/A | RFC
113 | 10-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/628 | N/A | N/A | TKV/COM/2025/658 | Response to Contractor's Submission of Excavation and Rock Support Design of Main Access Tunnel (Connecting Tunnel) - Drawing, Report & Reply - Comment | Attachment 1: Comment & Reply Sheet for Excavation and Rock Support Design of Main Access Tunnel (Connecting Tunnel) Drawing, Report (2 Pages). | N/A | Design | N/A | N/A | AAN
114 | 17-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/641 | N/A | LOT-01/SINOHYDRO-KSNS-JV/189 | TKV/COM/2025/637 | Engineer's Review, Comments, and Approval Status - Geological As - Built Drawing | N/A | TKV/COM/2025/697 TKV/COM/2025/706 TKV/COM/2025/725 TKV/COM/2025/735 TKV/COM/2025/741 | Design/Geology | N/A | N/A | Other
115 | 23-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/650 | N/A | N/A | TKV/COM/2025/689 | Response to Contractor’s Submission of Excavation and Rock Support Details for Adit - 4 Shop Drawings & Reply Comments | Comment & Reply Sheet for Excavation and Rock Support Details of Adit - 4 Shop Drawings & Reply Comments (1 Page). | N/A | Design | N/A | N/A | AAN
116 | 11-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/669 | N/A | N/A | TKV/COM/2026/699 | Structural Design Report (TKV-HMR-DD-IT-36-01_00) and Drawing (TKV-HMD-DD-IT-36C01_00) – Steel Lining, Inlet Transition Cone & Thrust Ring (Upstream of Penstock Protection Valve) – Technical Review Comments | N/A | N/A | Design | N/A | N/A | Other
117 | 11-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/673 | N/A | LOT-01/SINOHYDRO-KSNS-JV/584 LOT-01/SINOHYDRO-KSNS-JV/578 | TKV/COM/2026/709 | Response to Contractor’s Submission of Headrace Tunnel Excavation and Support Shop Drawing) | N/A | N/A | Design | N/A | N/A | RFC
118 | 13-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/675 | N/A | LOT-01/SINOHYDRO-KSNS-JV/572 | TKV/COM/2026/714 | Response to Contractor’s Submission of Excavation and Rock Support Escape Tunnel Shop Drawing | N/A | N/A | Design | N/A | N/A | RFC
119 | 13-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/677 | N/A | LOT-01/SINOHYDRO-KSNS-JV/615 LOT-01/SINOHYDRO-KSNS-JV/510 | TKV/COM/2026/712 TKV/COM/2025/606 TKV/COM/2025/530 | Response to Submission of Geotechnical Investigation Report for Headrace Tunnel and Contractor’s Response Comments | N/A | TKV/COM/2025/772 | Geology/Design | N/A | N/A | AAN
120 | 15-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/678 | N/A | N/A | TKV/COM/2026/717 | Response to Contractor’s Submission – Bus Duct Tunnel Excavation and Rock Support Shop Drawing & Response Comments | N/A | N/A | Design | N/A | N/A | RFC
121 | 15-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/680 | N/A | LOT-01/SINOHYDRO-KSNS-JV/259 | TKV/COM/2026/686 TKV/COM/2025/260 | Response to Contractor’s Early Warning Notice (Steel Lining for Pressure Tunnel and Shaft) | N/A | N/A | Contract/Design | N/A | N/A | Other
122 | 18-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/682 | N/A | N/A | TKV/COM/2026/690 | Response to Contractor’s Submission of CVT & Access to TRC Cavern Concrete and Reinforcement Shop Drawing | N/A | N/A | Design | N/A | N/A | RFC
123 | 18-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/683 | N/A | N/A | TKV/COM/2026/708 | Response to Submission of Main Access tunnel (Connectiong Tunnel) Rock Support hop Drawing and Response Comments | N/A | N/A | Design | N/A | N/A | Approved
124 | 26-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/693 | N/A | LOT-01/SINOHYDRO-KSNS-JV/642 | TKV/COM/2026/713 TKV/COM/2025/683 | Response to Submission of the Geotechnical Investigation Report for the Powerhouse Area | N/A | TKV/COM/2025/771 | Design/Geology | N/A | N/A | Other
125 | 26-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/694 | N/A | N/A | TKV/COM/2026/724 | Response to Contractor’s Submission Comment and Response Regarding Excavation and Support of Escape Tunnel Drawings and Report | Comment & Reply Sheet for Excavation and Support of Escape Tunnel Drawings and Report Support Shop Drawnig (2 Pages) | N/A | Design | N/A | N/A | RFC
126 | 27-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/699 | N/A | LOT-01/SINOHYDRO-KSNS-JV/630 | TKV/COM/2026/715 TKV/COM/2025/621 | Response to Submission of the Geotechnical Investigation Report for the Takeoff Yard and Bypass Area | N/A | TKV/COM/2025/773 | Design/Geology | N/A | N/A | AAN
127 | 28-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/700 | N/A | N/A | N/A | Request for Submission of Surface Geological Investigation Report | Annex-A sample outline of the Surface Geological investigation Report content | N/A | Design/Geology | N/A | N/A | Other
128 | 28-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/701 | N/A | LOT-01/SINOHYDRO-KSNS-JV/550 | TKV/COM/2026/703 TKV/COM/2024/556 | Response to Contractor's submission of Detailed Design-Headpond Structure Reinforcement, Concrete Drawings, Structural Analysis Report | Comment & Reply Sheet for Headpond Structure Concrete & Reinforcement shop Drawing (2 Pages) | TKV/COM/2025/765 | Design | N/A | N/A | Other
129 | 23-03-2026 | LOT-01/SINOHYDRO-KSNS-JV/727 | N/A | LOT-01/SINOHYDRO-KSNS-JV/720 | TKV/COM/2026/759 | Main Access Tunnel Portal Reinforcement Drawings - Review Pending Design Acceptance | N/A | N/A | Design | N/A | N/A | Other
130 | 27-03-2026 | LOT-01/SINOHYDRO-KSNS-JV/729 | N/A | N/A | TKV/COM/2026/769 | System Headloss and Plant Capacity Reassessment Report - Review Comments | N/A | N/A | Design | N/A | N/A | Other
131 | 30-03-2026 | LOT-01/SINOHYDRO-KSNS-JV/730 | N/A | N/A | TKV/COM/2026/763 | Response to Contractor’s Submission of Adit – 4 Valve House Cavern General Enlarged Tunnel Excavation and Support Details and Reply Comment | N/A | N/A | Design | N/A | N/A | AAN
132 | 03-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/731 | N/A | LOT-01/SINOHYDRO-KSNS-JV/677 LOT-01/SINOHYDRO-KSNS-JV/651 LOT-01/SINOHYDRO-KSNS-JV/615 LOT-01/SINOHYDRO-KSNS-JV/510 | TKV/COM/2026/772 TKV/COM/2026/712 TKV/COM/2026/606 TKV/COM/2025/530 | Response on Submission of Geotechnical Investigation Works of the Headrace Tunnel and Response Comment | N/A | N/A | Design | N/A | N/A | Resubmission Required
133 | 03-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/732 | N/A | LOT-01/SINOHYDRO-KSNS-JV/693 LOT-01/SINOHYDRO-KSNS-JV/642 | TKV/COM/2026/771 TKV/COM/2026/713 TKV/COM/2025/683 | Response on Submission of Geotechnical Investigation Works for the Powerhouse Area | N/A | N/A | Design | N/A | N/A | AAN
134 | 03-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/733 | N/A | LOT-01/SINOHYDRO-KSNS-JV/699 LOT-01/SINOHYDRO-KSNS-JV/630 | TKV/COM/2026/773 TKV/COM/2026/715 TKV/COM/2025/621 | Response on Submission of Geotechnical Investigation Works for the Takeoff Yard and Bypass Area | N/A | N/A | Design | N/A | N/A | Approved
135 | 04-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/734 | N/A | N/A | TKV/COM/2026/764 | Review of Submission on Structural Design of Spillway Terminal Structure – Returned for Correction (RFC) due to Non-Compliance with Specified Gate Type | N/A | N/A | Design | N/A | N/A | RFC
136 | 15-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/743 | N/A | LOT-01/SINOHYDRO-KSNS-JV/674 LOT-01/SINOHYDRO-KSNS-JV/643 | TKV/COM/2026/770 TKV/COM/2026/711 TKV/COM/2025/684 | Response on Submission of Geotechnical Investigation Work for the Headpond Area | N/A | N/A | Design | N/A | N/A | RFC
137 | 16-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/746 | N/A | N/A | TKV/COM/2026/765 | Approval of “Detail Design – Headpond Structure Reinforcement, Concrete Drawing, Structural Analysis Report” | Attachment 1: Comment & Reply Sheet for Detail Design–Headpond Structure Reinforcement, Concrete Drawing, Structural Analysis Report (2 Page). | N/A | Design | N/A | N/A | A
138 | 17-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/747 | N/A | N/A | TKV/COM/2026/786 | Response to Contractor’s Submission Regarding Comment and Response of General Arrangement and Excavation Support Design of Adit – 3 Portal | Attachment 1: Comment & Reply Sheet for General Arrangement and Excavation Support Design of Adit – 3 Portal (1 Page) | TKV/COM/2025/802 | Design | N/A | N/A | AAN
139 | 27-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/761 | N/A | N/A | TKV/COM/2026/792 | Response to Contractor’s Submission – Comment and Response of Excavation and Rock Support Drawings and Report for Adit-3 | Comment & Reply Sheet for Excavation and Rock Support Drawing and Report of Adit – 3 (2 Pages) | N/A | Design | N/A | N/A | AAN
140 | 29-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/768 | N/A | LOT-01/SINOHYDRO-KSNS-JV/739 LOT-01/SINOHYDRO-KSNS-JV/720 LOT-01/SINOHYDRO-KSNS-JV/690 LOT-01/SINOHYDRO-KSNS-JV/667 LOT-01/SINOHYDRO-KSNS-JV/638 LOT-01/SINOHYDRO-KSNS-JV/588 | TKV/COM/2026/799 TKV/COM/2026/774 TKV/COM/2026/752 TKV/COM/2025/743 TKV/COM/2026/734 TKV/COM/2026/729 TKV/COM/2025/669 TKV/COM/2026/603 | Response to Contractor’s Submission of Detailed Design – Main Access Tunnel Reinforcement, Concrete Lining Drawings, and Structural Analysis Report | Comment & Reply Sheet for Main Access Tunnel Concrete & Reinforcement Shop Drawings (13 Pages). | TKV/COM/2025/834 TKV/COM/2026/864 | Design | N/A | N/A | A
141 | 04-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/774 | N/A | LOT-01/SINOHYDRO-KSNS-JV/747 LOT-01/SINOHYDRO-KSNS-JV/725 | TKV/COM/2026/802 TKV/COM/2026/786 TKV/COM/2026/750 | Response to Contractor’s Submission of Comment and Response of Excavation Support Design of Adit – 3 Portal | N/A | N/A | Design | N/A | N/A | AAN
142 | 07-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/776 | N/A | N/A | N/A | Powerhouse Cavern and Transformer Cavern Layout Drawings (CAD) Required for Lot-2 Design Works | N/A | TKV/COM/2026/846 | Design | N/A | N/A | Other
143 | 09-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/781 | N/A | Lot-01/SINOHYDYO-KSNS-JV/700 | TKV/COM/2025/794 | Review of Surface Geological Investigation Report | Comment & Reply Sheet on the Surface Geological Investigation Report (6 Pages) | N/A | Design/Geology | N/A | N/A | RFC
144 | 15-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/791 | N/A | N/A | N/A | Transmittal of Request from Lot-2 Contractor's Design Consultant – Civil, Electrical and Mechanical Drawings and Documents Required for Lot-2 Design Works | N/A | N/A | Design | N/A | N/A | Other
145 | 15-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/792 | N/A | LOT-01/SINOHYDRO-KSNS/778 | TKV/COM/2024/837 | Response to Contractor’s Submission of Comment and Response Regarding Spillway Terminal Outlet Slope Protection Drawing and Report | Comment & Reply Sheet for Spillway Terminal Outlet Slope Protection Drawing and Report (2 pages) | N/A | Design | N/A | N/A | RFC
146 | 17-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/796 | N/A | Lot-01/Sinohydro-KSNS-JV/763 | TKV/COM/2026/823 TKV/COM/2026/781 | Response to the Contractor’s submission “Detail Design Report on Reassessment of Rock Support Analysis of Powerhouse Cavern with Lab and In-Situ Data | Attachment 1 – The Engineer’s Detailed Comments on the Contractor’s “Detail Design Report on the Reassessment of the Rock Support Analysis of the Powerhouse Cavern, with Laboratory and InSitu Data” (Document No.: TKV-CR-DD-RPH-01-01). | N/A | Design | N/A | N/A | RFC
147 | 22-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/802 | N/A | N/A | TKV/COM/2024/849 | Response to Contractor’s Submission of Powerhouse Adit Tunnel Drawing | : Comment & Reply Sheet for Powerhouse Adit Tunnel Drawing and Report (2 Pages). | N/A | Design | N/A | N/A | RFC
148 | 24-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/809 | N/A | N/A | TKV/COM/2026/839 | Design of Tailrace Gate – Required Corrective Measures | N/A | N/A | Design | N/A | N/A | Other
149 | 04-06-2026 | LOT-01/SINOHYDRO-KSNS-JV/827 | N/A | LOT-01/SINOHYDRO-KSNS-JV/827 | TKV/COM/2026/833 | Review of the Structural Design Report and Drawing for the Steel Lining — Inlet Transition Cone with Pipe and Thrust Ring (Upstream of the Penstock Protection Valve):Returned for Correction (RFC) | N/A | N/A | Design | N/A | N/A | Other
150 | 06-06-2026 | LOT-01/SINOHYDRO-KSNS-JV/831 | N/A | N/A | TKV/COM/2026/842 | Review of Main Access Tunnel Concrete and Reinforcement Shop Drawing – Drawing No. TKV-CD-SD-MAT-41C03, Rev.02 – Returned for Correction | Attachment-1 – Comments and Reply Sheet for Contractor’s letter Ref. TKV/COM/2026/842 dated 15 May 2026 2. Attachment-2 – Main Access Tunnel Concrete and Reinforcement Shop Drawing, Drawing No. TKV-CD-SD-MAT-41C03, Rev.02 (10 Sheets) | N/A | Design | N/A | N/A | RFC
151 | 10-06-2026 | LOT-01/SINOHYDRO-KSNS-JV/833 | N/A | N/A | TKV/COM/2026/855 | Hydraulic and Operational Risks Associated with the Tailrace Tunnel Outlet Design – Response to Letter Ref. TKV/COM/2026/855 | N/A | N/A | Contract/Design | N/A | N/A | Other

## Approval Summary
DESIGN DEPARTMENT – APPROVAL STATUS SUMMARY
S.No. | Status Category | Count | % of Total
1 | Approved | 9 | 6.0%
2 | Accept | 1 | 0.7%
3 | A | 14 | 9.3%
4 | AAN | 36 | 23.8%
5 | RFC | 27 | 17.9%
6 | Revision Required | 0 | 0.0%
7 | Resubmission Required | 1 | 0.7%
8 | Other | 63 | 41.7%
| TOTAL | 151 | 100.0%

## Excluded Records Log
EXCLUDED RECORDS LOG
S.No. | Send Date | Letter No. | Subject | Department | Status | Exclusion Reason
1 | 05-07-2024 | LOT-01/SINOHYDRO-KSNS-JV/026 | Submission of the Content of Basic Design for Review | Design | RFC | Replied RFC
2 | 04-09-2024 | LOT-01/SINOHYDRO-KSNS-JV/060 | Response to Regarding the Adit-3 Reports and Drawings of Portal & Tunnel | Design | RFC | Replied RFC
3 | 08-09-2024 | LOT-01/SINOHYDRO-KSNS-JV/063 | Review of the Detail Design Report for the Rock Support Analysis of Adit-1 | Geological/ Design | RFC | Replied RFC
4 | 04-10-2024 | LOT-01/SINOHYDRO-KSNS-JV/077 | Response to the Regarding the Adit-4 Repots and Drawings for Portal & Tunnel | Design | RFC | Replied RFC
5 | 19-10-2024 | LOT-01/SINOHYDRO-KSNS-JV/083 | Review of Contractor's Submission for MAT and CVT Reports and Drawings for Portal and Tunnel | Design | RFC | Replied RFC
6 | 24-10-2024 | LOT-01/SINOHYDRO-KSNS-JV/092 | Engineer's Review of Draft Basic Desiqn Report | Design | RFC | Replied RFC
7 | 12-12-2024 | LOT-01/SINOHYDRO-KSNS-JV/117 | Review of Regarding the Adit-2 Reports and Drawings for Portal and Tunnel. | Design | RFC | Replied RFC
8 | 13-01-2025 | LOT-01/SINOHYDRO-KSNS-JV/142 | Review of Adit-2_Reports and Drawings of Tunnel | Design | RFC | Replied RFC
9 | 29-01-2025 | LOT-01/SINOHYDRO-KSNS-JV/163 | Review of Contractor’s Submission – Cable Ventilation Tunnel (CVT) Drawing and Report | Design | RFC | Replied RFC
10 | 09-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/192 | Response to Closing NCR Regarding Unauthorized and Deviation of Materials used in tunnel support works | QC/QA/Design | RFC | Replied RFC
11 | 16-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/195 | Response to the Drawings and Report of Cable & Ventilation Tunnel | Design | RFC | Replied RFC
12 | 23-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/203 | Response to the Steel Lining Reports and Drawings for Pressure Tunnel and Shaft | Design | RFC | Replied RFC
13 | 24-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/204 | Response to the Drawing & Report of Adit-4 Tunnel. | Design | RFC | Replied RFC
14 | 30-03-2025 | LOT-01/SINOHYDRO-KSNS-JV/214 | Response to Submission of Reports and Drawings for Adit-2 Portal & Tunnel | Design | RFC | Replied RFC
15 | 06-06-2025 | LOT-01/SINOHYDRO-KSNS-JV/303 | Review of the Documents for Sub-milestone B.2. Attached to Interim Payment Statement-03 and Additional Information Required. | QA/Design/Contract | RFC | Replied RFC
16 | 09-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/350 | Response to Resubmission of Drawings and Reports of Powerhouse Cavern | Design | RFC | Replied RFC
17 | 10-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/354 | Response to Resubmission of Drawings and Report for Transformer Cavern | Design | RFC | Replied RFC
18 | 13-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/363 | Response to Submission of Drawing and Report of Rock Support for Power Station Tailrace Surge Tunnel | Design | RFC | Replied RFC
19 | 16-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/367 | Response to Submission of Shop Drawing of Adit-1 Tunnel Excavation and Rock Support | Design | RFC | Replied RFC
20 | 26-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/377 | Response to Resubmission of Drawings and Report for Transformer Cavern | Design | RFC | Replied RFC
21 | 28-07-2025 | LOT-01/SINOHYDRO-KSNS-JV/380 | Response to Submission of Detailed Design Report – Rock Support Analysis at Adit-1 Intersection | Geology/Design | RFC | Replied RFC
22 | 09-08-2025 | LOT-01/SINOHYDRO-KSNS-JV/399 | Response to Submission of Design Drawings and Reports for Valve House Cavern and VPS Top Cavern | Design | RFC | Replied RFC
23 | 21-09-2025 | LOT-01/SINOHYDRO-KSNS-JV/451 | Response to Contractor’s Submission of Excavation and Rock Support Design and Drawing of Upstream Manifold | Design | RFC | Replied RFC
24 | 29-10-2025 | LOT-01/SINOHYDRO-KSNS-JV/500 | Submission of Upstream Manifold Hydro-Mechanical Design Reports and Drawings | Design | RFC | Replied RFC
25 | 03-11-2025 | LOT-01/SINOHYDRO-KSNS-JV/510 | Comments on Geotechnical Investigation Report and Drawings for Headrace Tunnel (HRT). | Design/Geology | RFC | Replied RFC
26 | 09-11-2025 | LOT-01/SINOHYDRO-KSNS-JV/523 | Response to Contractor’s Submission of Bus Duct Tunnel Excavation and Support Drawing and Report | Design | RFC | Replied RFC
27 | 28-11-2025 | LOT-01/SINOHYDRO-KSNS-JV/550 | Submission of Headpond Structure Design Drawings and Report – Review Comments | Design | RFC | Replied RFC
28 | 30-11-2025 | LOT-01/SINOHYDRO-KSNS-JV/552 | Response to Contractor’s Submission of Main Access Tunnel (Connecting Tunnel) Excavation and Support Drawing and Report | Design | RFC | Replied RFC
29 | 12-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/564 | Response to Contractor’s Submission of Shop Drawing for Transformer Cavern Rock Support Details | Design | RFC | Replied RFC
30 | 12-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/565 | Response to Contractor’s Submission of Upstream Manifold Excavation and Rock Support Details Shop Drawing | Design | RFC | Replied RFC
31 | 12-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/566 | Response to Contractor’s Submission of Main Access Tunnel Shop Drawing | Design | RFC | Replied RFC
32 | 12-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/567 | Response to Contractor’s Submission of Headpond Shop Drawing | Design | RFC | Replied RFC
33 | 17-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/572 | Response to Contractor’s Submission of Excavation and Rock Support Escape Tunnel Drawings and Report | Design | RFC | Replied RFC
34 | 21-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/582 | Response to Contractor’s Submission of Power Station Powerhouse Cavern Rock Support Details Shop Drawing | Design | RFC | Replied RFC
35 | 24-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/588 | Response to Contractor's Submission of Main Access Tunnel Invert Detail Drawing | Design | Resubmission Required | Replied RFC
36 | 30-12-2025 | LOT-01/SINOHYDRO-KSNS-JV/604 | Response to Contractor's Submission of As-Built Drawing of Excavation and Rock Support fo Bus Duct Tunnel | Design | RFC | Replied RFC
37 | 04-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/615 | Engineer's Response to the Resubmission of the Geotechnical Investigation Report and Drawings for the Headrace Tunnel (HRT) | Design | RFC | Replied RFC
38 | 05-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/618 | Response to Contractor's Submission of Shop Drawing for Main Access Tunnel Support Details | Design | RFC | Replied RFC
39 | 05-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/619 | Response to Contractor's Submission of Main Access Tunnel (Connecting Tunnel) As - Built Drawing | Design | RFC | Replied RFC
40 | 10-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/629 | Response to Contractor's Submission of Excavation and Rock Support Details of Adit - 4 Shop Drawing | Design | RFC | Replied RFC
41 | 11-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/630 | Comments on Final Report on Geotechnical Investigation Works on Takeoff Yard and Bypass Yard | Design | RFC | Replied RFC
42 | 16-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/638 | Main Access Tunnel Reinforcement and Concrete Lining Drawing & Report - Engineer's Comments and Required Resubmission | Design | RFC | Replied RFC
43 | 19-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/642 | Response to Contractor's Submission of Geo-technical Investigation Work Report of Powerhouse Cavern | Design | RFC | Replied RFC
44 | 19-01-2026 | LOT-01/SINOHYDRO-KSNS-JV/643 | Response to Contractor's Submission of Geo-technical Investigation Work Report of Headpond | Design | RFC | Replied RFC
45 | 04-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/662 | Response to Contractor’s Submission of DCN and Adit – 4 Valve House Cavern – General Enlarged Tunnel Excavation and Support Detail Drawing. | Design | RFC | Replied RFC
46 | 04-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/665 | Response to Contractor’s Submission of Cable and Ventilation Tunnel Invert Detail Design | Design | RFC | Replied RFC
47 | 07-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/667 | Engineer’s Review of Contractor’s Submission – Main Access Tunnel Reinforcement & Concrete Lining and Invert Detail Design – Revision and Resubmission Required | Design | RFC | Replied RFC
48 | 13-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/674 | Response on Submission of the Geotechnical Investigation Report of Headpond and Contractor’s Response Comments | Geology/Design | RFC | Replied RFC
49 | 23-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/687 | Response to Contractor’s Submission Regarding Shop Drawing for Main Access Tunnel Support Details | Design | RFC | Replied RFC
50 | 24-02-2026 | LOT-01/SINOHYDRO-KSNS-JV/690 | Response to Contractor’s Submission of Detailed Design – Main Access Tunnel Lining and Invert Concrete & Reinforcement | Design | RFC | Replied RFC
51 | 08-03-2026 | LOT-01/SINOHYDRO-KSNS-JV/712 | Response to Contractor’s Submission of Detailed Design – Spillway Terminal Outlet Structure Reinforcement, Concrete Drawings, and Structural Analysis Report | Design | RFC | Replied RFC
52 | 10-03-2026 | LOT-01/SINOHYDRO-KSNS-JV/720 | Response to Contractor's Submission of Detailed Design - Main Access Tunnel Reinforcement, Concrete Drawings, and Structural Analysis Report | Design | RFC | Replied RFC
53 | 18-03-2026 | LOT-01/SINOHYDRO-KSNS-JV/725 | Respinse to Contractor's Submission Regarding - General Arrangement and Excavation Support Design of Adit-3 Portal (Report and Drawing) | Design | RFC | Replied RFC
54 | 27-03-2026 | LOT-01/SINOHYDRO-KSNS-JV/728 | Response to Contractor’s Submission Regarding Detail Design Report of Rock Support Analysis & Excavation and Rock Support Detail Drawing of Adit-3 | Design | RFC | Replied RFC
55 | 10-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/739 | Response to Contractor's Submission of Detailed Design - Main Access Tunnel Reinforcement, Concrete Lining Drawings, and Structural Analysis Report | Design | RFC | Replied RFC
56 | 27-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/763 | Response to Submission of Reassessment of Powerhouse Cavern Support Enhancement Drawing and Report | Design | Revision Required | Replied RFC
57 | 29-04-2026 | LOT-01/SINOHYDRO-KSNS-JV/767 | Response to Contractor’s Submission of Detail Design - Spillway Terminal Outlet Structure Reinforcement and Concrete Drawing and Report | Design | RFC | Replied RFC
58 | 07-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/778 | Response to Contractor’s Submission of Spillway Terminal Outlet Slope Protection Drawing | Design | RFC | Replied RFC
59 | 12-05-2026 | LOT-01/SINOHYDRO-KSNS-JV/786 | Review Comments on the Submission of Main Access Tunnel Concrete and Reinforcement Shop Drawing | Design | Revision Required | Replied RFC
60 | 04-06-2026 | LOT-01/SINOHYDRO-KSNS-JV/830 | Review of Headpond Structure Shop Drawing – Drawing No. TKV-CD-SD-HP23S01, Rev.00 – Returned for Correction | Design | RFC | Replied RFC